## Soothsayer Contingency
Soothsayer™ for Project Contingency |  |  |  |  | FULL Contingency | PARTIAL Contingency |  |  | ! ! ! VERY IMPORTANT ! ! !
After entering all tasks, sort columns A-D so the LARGEST At Risk values are displayed FIRST
ID | Maximum | Your Estimate | At Risk | Risk # | 73.724 | 27
1 | 130 | 110.0746 | 19.9254 | 1 | 19.9254 | 7 |  | With | 15 | project tasks,
2 | 104 | 88.0597 | 15.9403 | 2 | 15.9403 | 6 |  | where the average probability is | 80% | that each task will finish on-time or on-budget,
3 | 78 | 66.0448 | 11.9552 | 3 | 11.9552 | 4 |  | (meaning that each task has a | 20% | average risk of EXCEEDING Your Estimate
4 | 65 | 55.0373 | 9.9627 | 4 | 9.9627 | 4 |  |  |  | listed in column C),
5 | 52 | 44.0298 | 7.9702 | 5 | 7.9702 | 3 |  | you expect, with | 95% | confidence,
6 | 52 | 44.0298 | 7.9702 | 6 | 7.9702 | 3 |  | that no more than | 6 | tasks in your project will exceed Your Estimate
7 | 52 | 44.0298 | 7.9702 | 7 | [5 empty] | in column C.
8 | 39 | 33.0224 | 5.9776 | 8
9 | 39 | 33.0224 | 5.9776 | 9 |  |  |  | Put another way, there is a | 98.19% | probability that
10 | 39 | 33.0224 | 5.9776 | 10 |  |  |  |  | 6 | tasks, or fewer, will incur a schedule/budget failure
11 | 26 | 22.0149 | 3.9851 | 11 | [5 empty] | and finish later / cost more than you expected.
12 | 26 | 22.0149 | 3.9851 | 12 |  |  |  | The At Risk distribution is | 33% | Choose 50% as a conservative contingency
13 | 26 | 22.0149 | 3.9851 | 13 | [5 empty] | Choose 33% as a less-conservative contingency
14 | 26 | 22.0149 | 3.9851 | 14 | [5 empty] | Choose 25% as a near-minimum contingency
15 | 13 | 11.0075 | 1.9925 | 15 | [5 empty] | Choose 20% as a minimum contingency
16 |  |  | 0 | 16 |  |  | About Soothsayer™: Soothsayer is an Excel-based implementation of the Unified Scheduling Method, which is an approach to
17 |  |  | 0 | 17 |  |  | project buffering co-created by Drs. Denis Cioffi and Homayoun Khamooshi at the George Washington University. In one of their
18 |  |  | 0 | 18 |  |  | published articles, they advised using either 50% or 33% for the At Risk error distribution as convenient approximations.
19 |  |  | 0 | 19 |  |  | In my own research using project simulations, I have found that 20% and 25% were also a valid choices which came closer
20 |  |  | 0 | 20 |  |  | to simulated project outcomes than choosing either 50% or 33%. -- William W. Davis, MSPM, PMP
21 |  |  | 0 | 21
22 |  |  | 0 | 22
23 |  |  | 0 | 23
24 |  |  | 0 | 24
25 |  |  | 0 | 25
26 |  |  | 0 | 26
27 |  |  | 0 | 27
28 |  |  | 0 | 28
29 |  |  | 0 | 29
30 |  |  | 0 | 30
31 |  |  | 0 | 31
32 |  |  | 0 | 32
33 |  |  | 0 | 33
34 |  |  | 0 | 34
35 |  |  | 0 | 35
36 |  |  | 0 | 36
37 |  |  | 0 | 37
38 |  |  | 0 | 38
39 |  |  | 0 | 39
40 |  |  | 0 | 40
41 |  |  | 0 | 41
42 |  |  | 0 | 42
43 |  |  | 0 | 43
44 |  |  | 0 | 44
45 |  |  | 0 | 45
46 |  |  | 0 | 46
47 |  |  | 0 | 47
48 |  |  | 0 | 48
49 |  |  | 0 | 49
50 |  |  | 0 | 50
51 |  |  | 0 | 51
52 |  |  | 0 | 52
53 |  |  | 0 | 53
54 |  |  | 0 | 54
55 |  |  | 0 | 55
56 |  |  | 0 | 56
57 |  |  | 0 | 57
58 |  |  | 0 | 58
59 |  |  | 0 | 59
60 |  |  | 0 | 60
61 |  |  | 0 | 61
62 |  |  | 0 | 62
63 |  |  | 0 | 63
64 |  |  | 0 | 64
65 |  |  | 0 | 65
66 |  |  | 0 | 66
67 |  |  | 0 | 67
68 |  |  | 0 | 68
69 |  |  | 0 | 69
70 |  |  | 0 | 70
71 |  |  | 0 | 71
72 |  |  | 0 | 72
73 |  |  | 0 | 73
74 |  |  | 0 | 74
75 |  |  | 0 | 75
76 |  |  | 0 | 76
77 |  |  | 0 | 77
78 |  |  | 0 | 78
79 |  |  | 0 | 79
80 |  |  | 0 | 80
81 |  |  | 0 | 81
82 |  |  | 0 | 82
83 |  |  | 0 | 83
84 |  |  | 0 | 84
85 |  |  | 0 | 85
86 |  |  | 0 | 86
87 |  |  | 0 | 87
88 |  |  | 0 | 88
89 |  |  | 0 | 89
90 |  |  | 0 | 90
91 |  |  | 0 | 91
92 |  |  | 0 | 92
93 |  |  | 0 | 93
94 |  |  | 0 | 94
95 |  |  | 0 | 95
96 |  |  | 0 | 96
97 |  |  | 0 | 97
98 |  |  | 0 | 98
99 |  |  | 0 | 99
100 |  |  | 0 | 100
101 |  |  | 0 | 101
102 |  |  | 0 | 102
103 |  |  | 0 | 103
104 |  |  | 0 | 104
105 |  |  | 0 | 105
106 |  |  | 0 | 106
107 |  |  | 0 | 107
108 |  |  | 0 | 108
109 |  |  | 0 | 109
110 |  |  | 0 | 110
111 |  |  | 0 | 111
112 |  |  | 0 | 112
113 |  |  | 0 | 113
114 |  |  | 0 | 114
115 |  |  | 0 | 115
116 |  |  | 0 | 116
117 |  |  | 0 | 117
118 |  |  | 0 | 118
119 |  |  | 0 | 119
120 |  |  | 0 | 120
121 |  |  | 0 | 121
122 |  |  | 0 | 122
123 |  |  | 0 | 123
124 |  |  | 0 | 124
125 |  |  | 0 | 125
126 |  |  | 0 | 126
127 |  |  | 0 | 127
128 |  |  | 0 | 128
129 |  |  | 0 | 129
130 |  |  | 0 | 130
131 |  |  | 0 | 131
132 |  |  | 0 | 132
133 |  |  | 0 | 133
134 |  |  | 0 | 134
135 |  |  | 0 | 135
136 |  |  | 0 | 136
137 |  |  | 0 | 137
138 |  |  | 0 | 138
139 |  |  | 0 | 139
140 |  |  | 0 | 140
141 |  |  | 0 | 141
142 |  |  | 0 | 142
143 |  |  | 0 | 143
144 |  |  | 0 | 144
145 |  |  | 0 | 145
146 |  |  | 0 | 146
147 |  |  | 0 | 147
148 |  |  | 0 | 148
149 |  |  | 0 | 149
150 |  |  | 0 | 150
151 |  |  | 0 | 151
152 |  |  | 0 | 152
153 |  |  | 0 | 153
154 |  |  | 0 | 154
155 |  |  | 0 | 155
156 |  |  | 0 | 156
157 |  |  | 0 | 157
158 |  |  | 0 | 158
159 |  |  | 0 | 159
160 |  |  | 0 | 160
161 |  |  | 0 | 161
162 |  |  | 0 | 162
163 |  |  | 0 | 163
164 |  |  | 0 | 164
165 |  |  | 0 | 165
166 |  |  | 0 | 166
167 |  |  | 0 | 167
168 |  |  | 0 | 168
169 |  |  | 0 | 169
170 |  |  | 0 | 170
171 |  |  | 0 | 171
172 |  |  | 0 | 172
173 |  |  | 0 | 173
174 |  |  | 0 | 174
175 |  |  | 0 | 175
176 |  |  | 0 | 176
177 |  |  | 0 | 177
178 |  |  | 0 | 178
179 |  |  | 0 | 179
180 |  |  | 0 | 180
181 |  |  | 0 | 181
182 |  |  | 0 | 182
183 |  |  | 0 | 183
184 |  |  | 0 | 184
185 |  |  | 0 | 185
186 |  |  | 0 | 186
187 |  |  | 0 | 187
188 |  |  | 0 | 188
189 |  |  | 0 | 189
190 |  |  | 0 | 190
191 |  |  | 0 | 191
192 |  |  | 0 | 192
193 |  |  | 0 | 193
194 |  |  | 0 | 194
195 |  |  | 0 | 195
196 |  |  | 0 | 196
197 |  |  | 0 | 197
198 |  |  | 0 | 198
199 |  |  | 0 | 199
200 |  |  | 0 | 200
201 |  |  | 0 | 201
202 |  |  | 0 | 202
203 |  |  | 0 | 203
204 |  |  | 0 | 204
205 |  |  | 0 | 205
206 |  |  | 0 | 206
207 |  |  | 0 | 207
208 |  |  | 0 | 208
209 |  |  | 0 | 209
210 |  |  | 0 | 210
211 |  |  | 0 | 211
212 |  |  | 0 | 212
213 |  |  | 0 | 213
214 |  |  | 0 | 214
215 |  |  | 0 | 215
216 |  |  | 0 | 216
217 |  |  | 0 | 217
218 |  |  | 0 | 218
219 |  |  | 0 | 219
220 |  |  | 0 | 220
221 |  |  | 0 | 221
222 |  |  | 0 | 222
223 |  |  | 0 | 223
224 |  |  | 0 | 224
225 |  |  | 0 | 225
226 |  |  | 0 | 226
227 |  |  | 0 | 227
228 |  |  | 0 | 228
229 |  |  | 0 | 229
230 |  |  | 0 | 230
231 |  |  | 0 | 231
232 |  |  | 0 | 232
233 |  |  | 0 | 233
234 |  |  | 0 | 234
235 |  |  | 0 | 235
236 |  |  | 0 | 236
237 |  |  | 0 | 237
238 |  |  | 0 | 238
239 |  |  | 0 | 239
240 |  |  | 0 | 240
241 |  |  | 0 | 241
242 |  |  | 0 | 242
243 |  |  | 0 | 243
244 |  |  | 0 | 244
245 |  |  | 0 | 245
246 |  |  | 0 | 246
247 |  |  | 0 | 247
248 |  |  | 0 | 248
249 |  |  | 0 | 249
250 |  |  | 0 | 250
251 |  |  | 0 | 251
252 |  |  | 0 | 252
253 |  |  | 0 | 253
254 |  |  | 0 | 254
255 |  |  | 0 | 255
256 |  |  | 0 | 256
257 |  |  | 0 | 257
258 |  |  | 0 | 258
259 |  |  | 0 | 259
260 |  |  | 0 | 260
261 |  |  | 0 | 261
262 |  |  | 0 | 262
263 |  |  | 0 | 263
264 |  |  | 0 | 264
265 |  |  | 0 | 265
266 |  |  | 0 | 266
267 |  |  | 0 | 267
268 |  |  | 0 | 268
269 |  |  | 0 | 269
270 |  |  | 0 | 270
271 |  |  | 0 | 271
272 |  |  | 0 | 272
273 |  |  | 0 | 273
274 |  |  | 0 | 274
275 |  |  | 0 | 275
276 |  |  | 0 | 276
277 |  |  | 0 | 277
278 |  |  | 0 | 278
279 |  |  | 0 | 279
280 |  |  | 0 | 280
281 |  |  | 0 | 281
282 |  |  | 0 | 282
283 |  |  | 0 | 283
284 |  |  | 0 | 284
285 |  |  | 0 | 285
286 |  |  | 0 | 286
287 |  |  | 0 | 287
288 |  |  | 0 | 288
289 |  |  | 0 | 289
290 |  |  | 0 | 290
291 |  |  | 0 | 291
292 |  |  | 0 | 292
293 |  |  | 0 | 293
294 |  |  | 0 | 294
295 |  |  | 0 | 295
296 |  |  | 0 | 296
297 |  |  | 0 | 297
298 |  |  | 0 | 298
299 |  |  | 0 | 299
300 |  |  | 0 | 300
301 |  |  | 0 | 301
302 |  |  | 0 | 302
303 |  |  | 0 | 303
304 |  |  | 0 | 304
305 |  |  | 0 | 305
306 |  |  | 0 | 306
307 |  |  | 0 | 307
308 |  |  | 0 | 308
309 |  |  | 0 | 309
310 |  |  | 0 | 310
311 |  |  | 0 | 311
312 |  |  | 0 | 312
313 |  |  | 0 | 313
314 |  |  | 0 | 314
315 |  |  | 0 | 315
316 |  |  | 0 | 316
317 |  |  | 0 | 317
318 |  |  | 0 | 318
319 |  |  | 0 | 319
320 |  |  | 0 | 320
321 |  |  | 0 | 321
322 |  |  | 0 | 322
323 |  |  | 0 | 323
324 |  |  | 0 | 324
325 |  |  | 0 | 325
326 |  |  | 0 | 326
327 |  |  | 0 | 327
328 |  |  | 0 | 328
329 |  |  | 0 | 329
330 |  |  | 0 | 330
331 |  |  | 0 | 331
332 |  |  | 0 | 332
333 |  |  | 0 | 333
334 |  |  | 0 | 334
335 |  |  | 0 | 335
336 |  |  | 0 | 336
337 |  |  | 0 | 337
338 |  |  | 0 | 338
339 |  |  | 0 | 339
340 |  |  | 0 | 340
341 |  |  | 0 | 341
342 |  |  | 0 | 342
343 |  |  | 0 | 343
344 |  |  | 0 | 344
345 |  |  | 0 | 345
346 |  |  | 0 | 346
347 |  |  | 0 | 347
348 |  |  | 0 | 348
349 |  |  | 0 | 349
350 |  |  | 0 | 350
351 |  |  | 0 | 351
352 |  |  | 0 | 352
353 |  |  | 0 | 353
354 |  |  | 0 | 354
355 |  |  | 0 | 355
356 |  |  | 0 | 356
357 |  |  | 0 | 357
358 |  |  | 0 | 358
359 |  |  | 0 | 359
360 |  |  | 0 | 360
361 |  |  | 0 | 361
362 |  |  | 0 | 362
363 |  |  | 0 | 363
364 |  |  | 0 | 364
365 |  |  | 0 | 365
366 |  |  | 0 | 366
367 |  |  | 0 | 367
368 |  |  | 0 | 368
369 |  |  | 0 | 369
370 |  |  | 0 | 370
371 |  |  | 0 | 371
372 |  |  | 0 | 372
373 |  |  | 0 | 373
374 |  |  | 0 | 374
375 |  |  | 0 | 375
376 |  |  | 0 | 376
377 |  |  | 0 | 377
378 |  |  | 0 | 378
379 |  |  | 0 | 379
380 |  |  | 0 | 380
381 |  |  | 0 | 381
382 |  |  | 0 | 382
383 |  |  | 0 | 383
384 |  |  | 0 | 384
385 |  |  | 0 | 385
386 |  |  | 0 | 386
387 |  |  | 0 | 387
388 |  |  | 0 | 388
389 |  |  | 0 | 389
390 |  |  | 0 | 390
391 |  |  | 0 | 391
392 |  |  | 0 | 392
393 |  |  | 0 | 393
394 |  |  | 0 | 394
395 |  |  | 0 | 395
396 |  |  | 0 | 396
397 |  |  | 0 | 397
398 |  |  | 0 | 398
399 |  |  | 0 | 399
400 |  |  | 0 | 400
401 |  |  | 0 | 401
402 |  |  | 0 | 402
403 |  |  | 0 | 403
404 |  |  | 0 | 404
405 |  |  | 0 | 405
406 |  |  | 0 | 406
407 |  |  | 0 | 407
408 |  |  | 0 | 408
409 |  |  | 0 | 409
410 |  |  | 0 | 410
411 |  |  | 0 | 411
412 |  |  | 0 | 412
413 |  |  | 0 | 413
414 |  |  | 0 | 414
415 |  |  | 0 | 415
416 |  |  | 0 | 416
417 |  |  | 0 | 417
418 |  |  | 0 | 418
419 |  |  | 0 | 419
420 |  |  | 0 | 420
421 |  |  | 0 | 421
422 |  |  | 0 | 422
423 |  |  | 0 | 423
424 |  |  | 0 | 424
425 |  |  | 0 | 425
426 |  |  | 0 | 426
427 |  |  | 0 | 427
428 |  |  | 0 | 428
429 |  |  | 0 | 429
430 |  |  | 0 | 430
431 |  |  | 0 | 431
432 |  |  | 0 | 432
433 |  |  | 0 | 433
434 |  |  | 0 | 434
435 |  |  | 0 | 435
436 |  |  | 0 | 436
437 |  |  | 0 | 437
438 |  |  | 0 | 438
439 |  |  | 0 | 439
440 |  |  | 0 | 440
441 |  |  | 0 | 441
442 |  |  | 0 | 442
443 |  |  | 0 | 443
444 |  |  | 0 | 444
445 |  |  | 0 | 445
446 |  |  | 0 | 446
447 |  |  | 0 | 447
448 |  |  | 0 | 448
449 |  |  | 0 | 449
450 |  |  | 0 | 450
451 |  |  | 0 | 451
452 |  |  | 0 | 452
453 |  |  | 0 | 453
454 |  |  | 0 | 454
455 |  |  | 0 | 455
456 |  |  | 0 | 456
457 |  |  | 0 | 457
458 |  |  | 0 | 458
459 |  |  | 0 | 459
460 |  |  | 0 | 460
461 |  |  | 0 | 461
462 |  |  | 0 | 462
463 |  |  | 0 | 463
464 |  |  | 0 | 464
465 |  |  | 0 | 465
466 |  |  | 0 | 466
467 |  |  | 0 | 467
468 |  |  | 0 | 468
469 |  |  | 0 | 469
470 |  |  | 0 | 470
471 |  |  | 0 | 471
472 |  |  | 0 | 472
473 |  |  | 0 | 473
474 |  |  | 0 | 474
475 |  |  | 0 | 475
476 |  |  | 0 | 476
477 |  |  | 0 | 477
478 |  |  | 0 | 478
479 |  |  | 0 | 479
480 |  |  | 0 | 480
481 |  |  | 0 | 481
482 |  |  | 0 | 482
483 |  |  | 0 | 483
484 |  |  | 0 | 484
485 |  |  | 0 | 485
486 |  |  | 0 | 486
487 |  |  | 0 | 487
488 |  |  | 0 | 488
489 |  |  | 0 | 489
490 |  |  | 0 | 490
491 |  |  | 0 | 491
492 |  |  | 0 | 492
493 |  |  | 0 | 493
494 |  |  | 0 | 494
495 |  |  | 0 | 495
496 |  |  | 0 | 496
497 |  |  | 0 | 497
498 |  |  | 0 | 498
499 |  |  | 0 | 499
500 |  |  | 0 | 500
501 |  |  | 0 | 501
502 |  |  | 0 | 502
503 |  |  | 0 | 503
504 |  |  | 0 | 504
505 |  |  | 0 | 505
506 |  |  | 0 | 506
507 |  |  | 0 | 507
508 |  |  | 0 | 508
509 |  |  | 0 | 509
510 |  |  | 0 | 510
511 |  |  | 0 | 511
512 |  |  | 0 | 512
513 |  |  | 0 | 513
514 |  |  | 0 | 514
515 |  |  | 0 | 515
516 |  |  | 0 | 516
517 |  |  | 0 | 517
518 |  |  | 0 | 518
519 |  |  | 0 | 519
520 |  |  | 0 | 520
521 |  |  | 0 | 521
522 |  |  | 0 | 522
523 |  |  | 0 | 523
524 |  |  | 0 | 524
525 |  |  | 0 | 525
526 |  |  | 0 | 526
527 |  |  | 0 | 527
528 |  |  | 0 | 528
529 |  |  | 0 | 529
530 |  |  | 0 | 530
531 |  |  | 0 | 531
532 |  |  | 0 | 532
533 |  |  | 0 | 533
534 |  |  | 0 | 534
535 |  |  | 0 | 535
536 |  |  | 0 | 536
537 |  |  | 0 | 537
538 |  |  | 0 | 538
539 |  |  | 0 | 539
540 |  |  | 0 | 540
541 |  |  | 0 | 541
542 |  |  | 0 | 542
543 |  |  | 0 | 543
544 |  |  | 0 | 544
545 |  |  | 0 | 545
546 |  |  | 0 | 546
547 |  |  | 0 | 547
548 |  |  | 0 | 548
549 |  |  | 0 | 549
550 |  |  | 0 | 550
551 |  |  | 0 | 551
552 |  |  | 0 | 552
553 |  |  | 0 | 553
554 |  |  | 0 | 554
555 |  |  | 0 | 555
556 |  |  | 0 | 556
557 |  |  | 0 | 557
558 |  |  | 0 | 558
559 |  |  | 0 | 559
560 |  |  | 0 | 560
561 |  |  | 0 | 561
562 |  |  | 0 | 562
563 |  |  | 0 | 563
564 |  |  | 0 | 564
565 |  |  | 0 | 565
566 |  |  | 0 | 566
567 |  |  | 0 | 567
568 |  |  | 0 | 568
569 |  |  | 0 | 569
570 |  |  | 0 | 570
571 |  |  | 0 | 571
572 |  |  | 0 | 572
573 |  |  | 0 | 573
574 |  |  | 0 | 574
575 |  |  | 0 | 575
576 |  |  | 0 | 576
577 |  |  | 0 | 577
578 |  |  | 0 | 578
579 |  |  | 0 | 579
580 |  |  | 0 | 580
581 |  |  | 0 | 581
582 |  |  | 0 | 582
583 |  |  | 0 | 583
584 |  |  | 0 | 584
585 |  |  | 0 | 585
586 |  |  | 0 | 586
587 |  |  | 0 | 587
588 |  |  | 0 | 588
589 |  |  | 0 | 589
590 |  |  | 0 | 590
591 |  |  | 0 | 591
592 |  |  | 0 | 592
593 |  |  | 0 | 593
594 |  |  | 0 | 594
595 |  |  | 0 | 595
596 |  |  | 0 | 596
597 |  |  | 0 | 597
598 |  |  | 0 | 598
599 |  |  | 0 | 599
600 |  |  | 0 | 600
601 |  |  | 0 | 601
602 |  |  | 0 | 602
603 |  |  | 0 | 603
604 |  |  | 0 | 604
605 |  |  | 0 | 605
606 |  |  | 0 | 606
607 |  |  | 0 | 607
608 |  |  | 0 | 608
609 |  |  | 0 | 609
610 |  |  | 0 | 610
611 |  |  | 0 | 611
612 |  |  | 0 | 612
613 |  |  | 0 | 613
614 |  |  | 0 | 614
615 |  |  | 0 | 615
616 |  |  | 0 | 616
617 |  |  | 0 | 617
618 |  |  | 0 | 618
619 |  |  | 0 | 619
620 |  |  | 0 | 620
621 |  |  | 0 | 621
622 |  |  | 0 | 622
623 |  |  | 0 | 623
624 |  |  | 0 | 624
625 |  |  | 0 | 625
626 |  |  | 0 | 626
627 |  |  | 0 | 627
628 |  |  | 0 | 628
629 |  |  | 0 | 629
630 |  |  | 0 | 630
631 |  |  | 0 | 631
632 |  |  | 0 | 632
633 |  |  | 0 | 633
634 |  |  | 0 | 634
635 |  |  | 0 | 635
636 |  |  | 0 | 636
637 |  |  | 0 | 637
638 |  |  | 0 | 638
639 |  |  | 0 | 639
640 |  |  | 0 | 640
641 |  |  | 0 | 641
642 |  |  | 0 | 642
643 |  |  | 0 | 643
644 |  |  | 0 | 644
645 |  |  | 0 | 645
646 |  |  | 0 | 646
647 |  |  | 0 | 647
648 |  |  | 0 | 648
649 |  |  | 0 | 649
650 |  |  | 0 | 650
651 |  |  | 0 | 651
652 |  |  | 0 | 652
653 |  |  | 0 | 653
654 |  |  | 0 | 654
655 |  |  | 0 | 655
656 |  |  | 0 | 656
657 |  |  | 0 | 657
658 |  |  | 0 | 658
659 |  |  | 0 | 659
660 |  |  | 0 | 660
661 |  |  | 0 | 661
662 |  |  | 0 | 662
663 |  |  | 0 | 663
664 |  |  | 0 | 664
665 |  |  | 0 | 665
666 |  |  | 0 | 666
667 |  |  | 0 | 667
668 |  |  | 0 | 668
669 |  |  | 0 | 669
670 |  |  | 0 | 670
671 |  |  | 0 | 671
672 |  |  | 0 | 672
673 |  |  | 0 | 673
674 |  |  | 0 | 674
675 |  |  | 0 | 675
676 |  |  | 0 | 676
677 |  |  | 0 | 677
678 |  |  | 0 | 678
679 |  |  | 0 | 679
680 |  |  | 0 | 680
681 |  |  | 0 | 681
682 |  |  | 0 | 682
683 |  |  | 0 | 683
684 |  |  | 0 | 684
685 |  |  | 0 | 685
686 |  |  | 0 | 686
687 |  |  | 0 | 687
688 |  |  | 0 | 688
689 |  |  | 0 | 689
690 |  |  | 0 | 690
691 |  |  | 0 | 691
692 |  |  | 0 | 692
693 |  |  | 0 | 693
694 |  |  | 0 | 694
695 |  |  | 0 | 695
696 |  |  | 0 | 696
697 |  |  | 0 | 697
698 |  |  | 0 | 698
699 |  |  | 0 | 699
700 |  |  | 0 | 700
701 |  |  | 0 | 701
702 |  |  | 0 | 702
703 |  |  | 0 | 703
704 |  |  | 0 | 704
705 |  |  | 0 | 705
706 |  |  | 0 | 706
707 |  |  | 0 | 707
708 |  |  | 0 | 708
709 |  |  | 0 | 709
710 |  |  | 0 | 710
711 |  |  | 0 | 711
712 |  |  | 0 | 712
713 |  |  | 0 | 713
714 |  |  | 0 | 714
715 |  |  | 0 | 715
716 |  |  | 0 | 716
717 |  |  | 0 | 717
718 |  |  | 0 | 718
719 |  |  | 0 | 719
720 |  |  | 0 | 720
721 |  |  | 0 | 721
722 |  |  | 0 | 722
723 |  |  | 0 | 723
724 |  |  | 0 | 724
725 |  |  | 0 | 725
726 |  |  | 0 | 726
727 |  |  | 0 | 727
728 |  |  | 0 | 728
729 |  |  | 0 | 729
730 |  |  | 0 | 730
731 |  |  | 0 | 731
732 |  |  | 0 | 732
733 |  |  | 0 | 733
734 |  |  | 0 | 734
735 |  |  | 0 | 735
736 |  |  | 0 | 736
737 |  |  | 0 | 737
738 |  |  | 0 | 738
739 |  |  | 0 | 739
740 |  |  | 0 | 740
741 |  |  | 0 | 741
742 |  |  | 0 | 742
743 |  |  | 0 | 743
744 |  |  | 0 | 744
745 |  |  | 0 | 745
746 |  |  | 0 | 746
747 |  |  | 0 | 747
748 |  |  | 0 | 748
749 |  |  | 0 | 749
750 |  |  | 0 | 750
751 |  |  | 0 | 751
752 |  |  | 0 | 752
753 |  |  | 0 | 753
754 |  |  | 0 | 754
755 |  |  | 0 | 755
756 |  |  | 0 | 756
757 |  |  | 0 | 757
758 |  |  | 0 | 758
759 |  |  | 0 | 759
760 |  |  | 0 | 760
761 |  |  | 0 | 761
762 |  |  | 0 | 762
763 |  |  | 0 | 763
764 |  |  | 0 | 764
765 |  |  | 0 | 765
766 |  |  | 0 | 766
767 |  |  | 0 | 767
768 |  |  | 0 | 768
769 |  |  | 0 | 769
770 |  |  | 0 | 770
771 |  |  | 0 | 771
772 |  |  | 0 | 772
773 |  |  | 0 | 773
774 |  |  | 0 | 774
775 |  |  | 0 | 775
776 |  |  | 0 | 776
777 |  |  | 0 | 777
778 |  |  | 0 | 778
779 |  |  | 0 | 779
780 |  |  | 0 | 780
781 |  |  | 0 | 781
782 |  |  | 0 | 782
783 |  |  | 0 | 783
784 |  |  | 0 | 784
785 |  |  | 0 | 785
786 |  |  | 0 | 786
787 |  |  | 0 | 787
788 |  |  | 0 | 788
789 |  |  | 0 | 789
790 |  |  | 0 | 790
791 |  |  | 0 | 791
792 |  |  | 0 | 792
793 |  |  | 0 | 793
794 |  |  | 0 | 794
795 |  |  | 0 | 795
796 |  |  | 0 | 796
797 |  |  | 0 | 797
798 |  |  | 0 | 798
799 |  |  | 0 | 799
800 |  |  | 0 | 800
801 |  |  | 0 | 801
802 |  |  | 0 | 802
803 |  |  | 0 | 803
804 |  |  | 0 | 804
805 |  |  | 0 | 805
806 |  |  | 0 | 806
807 |  |  | 0 | 807
808 |  |  | 0 | 808
809 |  |  | 0 | 809
810 |  |  | 0 | 810
811 |  |  | 0 | 811
812 |  |  | 0 | 812
813 |  |  | 0 | 813
814 |  |  | 0 | 814
815 |  |  | 0 | 815
816 |  |  | 0 | 816
817 |  |  | 0 | 817
818 |  |  | 0 | 818
819 |  |  | 0 | 819
820 |  |  | 0 | 820
821 |  |  | 0 | 821
822 |  |  | 0 | 822
823 |  |  | 0 | 823
824 |  |  | 0 | 824
825 |  |  | 0 | 825
826 |  |  | 0 | 826
827 |  |  | 0 | 827
828 |  |  | 0 | 828
829 |  |  | 0 | 829
830 |  |  | 0 | 830
831 |  |  | 0 | 831
832 |  |  | 0 | 832
833 |  |  | 0 | 833
834 |  |  | 0 | 834
835 |  |  | 0 | 835
836 |  |  | 0 | 836
837 |  |  | 0 | 837
838 |  |  | 0 | 838
839 |  |  | 0 | 839
840 |  |  | 0 | 840
841 |  |  | 0 | 841
842 |  |  | 0 | 842
843 |  |  | 0 | 843
844 |  |  | 0 | 844
845 |  |  | 0 | 845
846 |  |  | 0 | 846
847 |  |  | 0 | 847
848 |  |  | 0 | 848
849 |  |  | 0 | 849
850 |  |  | 0 | 850
851 |  |  | 0 | 851
852 |  |  | 0 | 852
853 |  |  | 0 | 853
854 |  |  | 0 | 854
855 |  |  | 0 | 855
856 |  |  | 0 | 856
857 |  |  | 0 | 857
858 |  |  | 0 | 858
859 |  |  | 0 | 859
860 |  |  | 0 | 860
861 |  |  | 0 | 861
862 |  |  | 0 | 862
863 |  |  | 0 | 863
864 |  |  | 0 | 864
865 |  |  | 0 | 865
866 |  |  | 0 | 866
867 |  |  | 0 | 867
868 |  |  | 0 | 868
869 |  |  | 0 | 869
870 |  |  | 0 | 870
871 |  |  | 0 | 871
872 |  |  | 0 | 872
873 |  |  | 0 | 873
874 |  |  | 0 | 874
875 |  |  | 0 | 875
876 |  |  | 0 | 876
877 |  |  | 0 | 877
878 |  |  | 0 | 878
879 |  |  | 0 | 879
880 |  |  | 0 | 880
881 |  |  | 0 | 881
882 |  |  | 0 | 882
883 |  |  | 0 | 883
884 |  |  | 0 | 884
885 |  |  | 0 | 885
886 |  |  | 0 | 886
887 |  |  | 0 | 887
888 |  |  | 0 | 888
889 |  |  | 0 | 889
890 |  |  | 0 | 890
891 |  |  | 0 | 891
892 |  |  | 0 | 892
893 |  |  | 0 | 893
894 |  |  | 0 | 894
895 |  |  | 0 | 895
896 |  |  | 0 | 896
897 |  |  | 0 | 897
898 |  |  | 0 | 898
899 |  |  | 0 | 899
900 |  |  | 0 | 900
901 |  |  | 0 | 901
902 |  |  | 0 | 902
903 |  |  | 0 | 903
904 |  |  | 0 | 904
905 |  |  | 0 | 905
906 |  |  | 0 | 906
907 |  |  | 0 | 907
908 |  |  | 0 | 908
909 |  |  | 0 | 909
910 |  |  | 0 | 910
911 |  |  | 0 | 911
912 |  |  | 0 | 912
913 |  |  | 0 | 913
914 |  |  | 0 | 914
915 |  |  | 0 | 915
916 |  |  | 0 | 916
917 |  |  | 0 | 917
918 |  |  | 0 | 918
919 |  |  | 0 | 919
920 |  |  | 0 | 920
921 |  |  | 0 | 921
922 |  |  | 0 | 922
923 |  |  | 0 | 923
924 |  |  | 0 | 924
925 |  |  | 0 | 925
926 |  |  | 0 | 926
927 |  |  | 0 | 927
928 |  |  | 0 | 928
929 |  |  | 0 | 929
930 |  |  | 0 | 930
931 |  |  | 0 | 931
932 |  |  | 0 | 932
933 |  |  | 0 | 933
934 |  |  | 0 | 934
935 |  |  | 0 | 935
936 |  |  | 0 | 936
937 |  |  | 0 | 937
938 |  |  | 0 | 938
939 |  |  | 0 | 939
940 |  |  | 0 | 940
941 |  |  | 0 | 941
942 |  |  | 0 | 942
943 |  |  | 0 | 943
944 |  |  | 0 | 944
945 |  |  | 0 | 945
946 |  |  | 0 | 946
947 |  |  | 0 | 947
948 |  |  | 0 | 948
949 |  |  | 0 | 949
950 |  |  | 0 | 950
951 |  |  | 0 | 951
952 |  |  | 0 | 952
953 |  |  | 0 | 953
954 |  |  | 0 | 954
955 |  |  | 0 | 955
956 |  |  | 0 | 956
957 |  |  | 0 | 957
958 |  |  | 0 | 958
959 |  |  | 0 | 959
960 |  |  | 0 | 960
961 |  |  | 0 | 961
962 |  |  | 0 | 962
963 |  |  | 0 | 963
964 |  |  | 0 | 964
965 |  |  | 0 | 965
966 |  |  | 0 | 966
967 |  |  | 0 | 967
968 |  |  | 0 | 968
969 |  |  | 0 | 969
970 |  |  | 0 | 970
971 |  |  | 0 | 971
972 |  |  | 0 | 972
973 |  |  | 0 | 973
974 |  |  | 0 | 974
975 |  |  | 0 | 975
976 |  |  | 0 | 976
977 |  |  | 0 | 977
978 |  |  | 0 | 978
979 |  |  | 0 | 979
980 |  |  | 0 | 980
981 |  |  | 0 | 981
982 |  |  | 0 | 982
983 |  |  | 0 | 983
984 |  |  | 0 | 984
985 |  |  | 0 | 985
986 |  |  | 0 | 986
987 |  |  | 0 | 987
988 |  |  | 0 | 988
989 |  |  | 0 | 989
990 |  |  | 0 | 990
991 |  |  | 0 | 991
992 |  |  | 0 | 992
993 |  |  | 0 | 993
994 |  |  | 0 | 994
995 |  |  | 0 | 995
996 |  |  | 0 | 996
997 |  |  | 0 | 997
998 |  |  | 0 | 998
999 |  |  | 0 | 999
1000 |  |  | 0 | 1000
| 767 | 649.4401 | 117.5599
Rows 24 through 1003 are hidden - unhide these rows to add more tasks
Version 1.3 – © 2016-2020, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for monthly tips, free webinars, and new release notifications
Soothsayer™ is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Soothsayer™ is a non-federally-registered trademark. If you modify
this spreadsheet in any material way, please remove this trademarked name from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (http://www.gnu.org/licenses/).

## Change Log
Soothsayer™ for Project Contingency Change Log
Date | Version | Description
2020-07-09 | 1.3 | Changed Partial Contingency to use ROUNDUP function, updated footer link and file properties
2020-04-26 | 1.2 | Added author's note about using 25% as a minimum At Risk distribution value
2019-09-28 | 1.1 | Extended the task entry from 200 to 1000
2019-07-01 | 1.0.2 | Included full text of the GNU GPL, and updated the footer information
2017-06-10 | 1.0.1 | Changed labels to conform to AACE definition of project 'contingeny' (instead of 'reserve')
2016-10-07 | 1.0 | Initial release

## GNU GPL
GNU GENERAL PUBLIC LICENSE
Version 3, 29 June 2007
Copyright (C) 2007 Free Software Foundation, Inc. <https://fsf.org/>
Everyone is permitted to copy and distribute verbatim copies
of this license document, but changing it is not allowed.
Preamble
The GNU General Public License is a free, copyleft license for
software and other kinds of works.
The licenses for most software and other practical works are designed
to take away your freedom to share and change the works. By contrast,
the GNU General Public License is intended to guarantee your freedom to
share and change all versions of a program--to make sure it remains free
software for all its users. We, the Free Software Foundation, use the
GNU General Public License for most of our software; it applies also to
any other work released this way by its authors. You can apply it to
your programs, too.
When we speak of free software, we are referring to freedom, not
price. Our General Public Licenses are designed to make sure that you
have the freedom to distribute copies of free software (and charge for
them if you wish), that you receive source code or can get it if you
want it, that you can change the software or use pieces of it in new
free programs, and that you know you can do these things.
To protect your rights, we need to prevent others from denying you
these rights or asking you to surrender the rights. Therefore, you have
certain responsibilities if you distribute copies of the software, or if
you modify it: responsibilities to respect the freedom of others.
For example, if you distribute copies of such a program, whether
gratis or for a fee, you must pass on to the recipients the same
freedoms that you received. You must make sure that they, too, receive
or can get the source code. And you must show them these terms so they
know their rights.
Developers that use the GNU GPL protect your rights with two steps:
(1) assert copyright on the software, and (2) offer you this License
giving you legal permission to copy, distribute and/or modify it.
For the developers' and authors' protection, the GPL clearly explains
that there is no warranty for this free software. For both users' and
authors' sake, the GPL requires that modified versions be marked as
changed, so that their problems will not be attributed erroneously to
authors of previous versions.
Some devices are designed to deny users access to install or run
modified versions of the software inside them, although the manufacturer
can do so. This is fundamentally incompatible with the aim of
protecting users' freedom to change the software. The systematic
pattern of such abuse occurs in the area of products for individuals to
use, which is precisely where it is most unacceptable. Therefore, we
have designed this version of the GPL to prohibit the practice for those
products. If such problems arise substantially in other domains, we
stand ready to extend this provision to those domains in future versions
of the GPL, as needed to protect the freedom of users.
Finally, every program is threatened constantly by software patents.
States should not allow patents to restrict development and use of
software on general-purpose computers, but in those that do, we wish to
avoid the special danger that patents applied to a free program could
make it effectively proprietary. To prevent this, the GPL assures that
patents cannot be used to render the program non-free.
The precise terms and conditions for copying, distribution and
modification follow.
TERMS AND CONDITIONS
0. Definitions.
"This License" refers to version 3 of the GNU General Public License.
"Copyright" also means copyright-like laws that apply to other kinds of
works, such as semiconductor masks.
"The Program" refers to any copyrightable work licensed under this
License. Each licensee is addressed as "you". "Licensees" and
"recipients" may be individuals or organizations.
To "modify" a work means to copy from or adapt all or part of the work
in a fashion requiring copyright permission, other than the making of an
exact copy. The resulting work is called a "modified version" of the
earlier work or a work "based on" the earlier work.
A "covered work" means either the unmodified Program or a work based
on the Program.
To "propagate" a work means to do anything with it that, without
permission, would make you directly or secondarily liable for
infringement under applicable copyright law, except executing it on a
computer or modifying a private copy. Propagation includes copying,
distribution (with or without modification), making available to the
public, and in some countries other activities as well.
To "convey" a work means any kind of propagation that enables other
parties to make or receive copies. Mere interaction with a user through
a computer network, with no transfer of a copy, is not conveying.
An interactive user interface displays "Appropriate Legal Notices"
to the extent that it includes a convenient and prominently visible
feature that (1) displays an appropriate copyright notice, and (2)
tells the user that there is no warranty for the work (except to the
extent that warranties are provided), that licensees may convey the
work under this License, and how to view a copy of this License. If
the interface presents a list of user commands or options, such as a
menu, a prominent item in the list meets this criterion.
1. Source Code.
The "source code" for a work means the preferred form of the work
for making modifications to it. "Object code" means any non-source
form of a work.
A "Standard Interface" means an interface that either is an official
standard defined by a recognized standards body, or, in the case of
interfaces specified for a particular programming language, one that
is widely used among developers working in that language.
The "System Libraries" of an executable work include anything, other
than the work as a whole, that (a) is included in the normal form of
packaging a Major Component, but which is not part of that Major
Component, and (b) serves only to enable use of the work with that
Major Component, or to implement a Standard Interface for which an
implementation is available to the public in source code form. A
"Major Component", in this context, means a major essential component
(kernel, window system, and so on) of the specific operating system
(if any) on which the executable work runs, or a compiler used to
produce the work, or an object code interpreter used to run it.
The "Corresponding Source" for a work in object code form means all
the source code needed to generate, install, and (for an executable
work) run the object code and to modify the work, including scripts to
control those activities. However, it does not include the work's
System Libraries, or general-purpose tools or generally available free
programs which are used unmodified in performing those activities but
which are not part of the work. For example, Corresponding Source
includes interface definition files associated with source files for
the work, and the source code for shared libraries and dynamically
linked subprograms that the work is specifically designed to require,
such as by intimate data communication or control flow between those
subprograms and other parts of the work.
The Corresponding Source need not include anything that users
can regenerate automatically from other parts of the Corresponding
Source.
The Corresponding Source for a work in source code form is that
same work.
2. Basic Permissions.
All rights granted under this License are granted for the term of
copyright on the Program, and are irrevocable provided the stated
conditions are met. This License explicitly affirms your unlimited
permission to run the unmodified Program. The output from running a
covered work is covered by this License only if the output, given its
content, constitutes a covered work. This License acknowledges your
rights of fair use or other equivalent, as provided by copyright law.
You may make, run and propagate covered works that you do not
convey, without conditions so long as your license otherwise remains
in force. You may convey covered works to others for the sole purpose
of having them make modifications exclusively for you, or provide you
with facilities for running those works, provided that you comply with
the terms of this License in conveying all material for which you do
not control copyright. Those thus making or running the covered works
for you must do so exclusively on your behalf, under your direction
and control, on terms that prohibit them from making any copies of
your copyrighted material outside their relationship with you.
Conveying under any other circumstances is permitted solely under
the conditions stated below. Sublicensing is not allowed; section 10
makes it unnecessary.
3. Protecting Users' Legal Rights From Anti-Circumvention Law.
No covered work shall be deemed part of an effective technological
measure under any applicable law fulfilling obligations under article
11 of the WIPO copyright treaty adopted on 20 December 1996, or
similar laws prohibiting or restricting circumvention of such
measures.
When you convey a covered work, you waive any legal power to forbid
circumvention of technological measures to the extent such circumvention
is effected by exercising rights under this License with respect to
the covered work, and you disclaim any intention to limit operation or
modification of the work as a means of enforcing, against the work's
users, your or third parties' legal rights to forbid circumvention of
technological measures.
4. Conveying Verbatim Copies.
You may convey verbatim copies of the Program's source code as you
receive it, in any medium, provided that you conspicuously and
appropriately publish on each copy an appropriate copyright notice;
keep intact all notices stating that this License and any
non-permissive terms added in accord with section 7 apply to the code;
keep intact all notices of the absence of any warranty; and give all
recipients a copy of this License along with the Program.
You may charge any price or no price for each copy that you convey,
and you may offer support or warranty protection for a fee.
5. Conveying Modified Source Versions.
You may convey a work based on the Program, or the modifications to
produce it from the Program, in the form of source code under the
terms of section 4, provided that you also meet all of these conditions:
a) The work must carry prominent notices stating that you modified
it, and giving a relevant date.
b) The work must carry prominent notices stating that it is
released under this License and any conditions added under section
7. This requirement modifies the requirement in section 4 to
"keep intact all notices".
c) You must license the entire work, as a whole, under this
License to anyone who comes into possession of a copy. This
License will therefore apply, along with any applicable section 7
additional terms, to the whole of the work, and all its parts,
regardless of how they are packaged. This License gives no
permission to license the work in any other way, but it does not
invalidate such permission if you have separately received it.
d) If the work has interactive user interfaces, each must display
Appropriate Legal Notices; however, if the Program has interactive
interfaces that do not display Appropriate Legal Notices, your
work need not make them do so.
A compilation of a covered work with other separate and independent
works, which are not by their nature extensions of the covered work,
and which are not combined with it such as to form a larger program,
in or on a volume of a storage or distribution medium, is called an
"aggregate" if the compilation and its resulting copyright are not
used to limit the access or legal rights of the compilation's users
beyond what the individual works permit. Inclusion of a covered work
in an aggregate does not cause this License to apply to the other
parts of the aggregate.
6. Conveying Non-Source Forms.
You may convey a covered work in object code form under the terms
of sections 4 and 5, provided that you also convey the
machine-readable Corresponding Source under the terms of this License,
in one of these ways:
a) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by the
Corresponding Source fixed on a durable physical medium
customarily used for software interchange.
b) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by a
written offer, valid for at least three years and valid for as
long as you offer spare parts or customer support for that product
model, to give anyone who possesses the object code either (1) a
copy of the Corresponding Source for all the software in the
product that is covered by this License, on a durable physical
medium customarily used for software interchange, for a price no
more than your reasonable cost of physically performing this
conveying of source, or (2) access to copy the
Corresponding Source from a network server at no charge.
c) Convey individual copies of the object code with a copy of the
written offer to provide the Corresponding Source. This
alternative is allowed only occasionally and noncommercially, and
only if you received the object code with such an offer, in accord
with subsection 6b.
d) Convey the object code by offering access from a designated
place (gratis or for a charge), and offer equivalent access to the
Corresponding Source in the same way through the same place at no
further charge. You need not require recipients to copy the
Corresponding Source along with the object code. If the place to
copy the object code is a network server, the Corresponding Source
may be on a different server (operated by you or a third party)
that supports equivalent copying facilities, provided you maintain
clear directions next to the object code saying where to find the
Corresponding Source. Regardless of what server hosts the
Corresponding Source, you remain obligated to ensure that it is
available for as long as needed to satisfy these requirements.
e) Convey the object code using peer-to-peer transmission, provided
you inform other peers where the object code and Corresponding
Source of the work are being offered to the general public at no
charge under subsection 6d.
A separable portion of the object code, whose source code is excluded
from the Corresponding Source as a System Library, need not be
included in conveying the object code work.
A "User Product" is either (1) a "consumer product", which means any
tangible personal property which is normally used for personal, family,
or household purposes, or (2) anything designed or sold for incorporation
into a dwelling. In determining whether a product is a consumer product,
doubtful cases shall be resolved in favor of coverage. For a particular
product received by a particular user, "normally used" refers to a
typical or common use of that class of product, regardless of the status
of the particular user or of the way in which the particular user
actually uses, or expects or is expected to use, the product. A product
is a consumer product regardless of whether the product has substantial
commercial, industrial or non-consumer uses, unless such uses represent
the only significant mode of use of the product.
"Installation Information" for a User Product means any methods,
procedures, authorization keys, or other information required to install
and execute modified versions of a covered work in that User Product from
a modified version of its Corresponding Source. The information must
suffice to ensure that the continued functioning of the modified object
code is in no case prevented or interfered with solely because
modification has been made.
If you convey an object code work under this section in, or with, or
specifically for use in, a User Product, and the conveying occurs as
part of a transaction in which the right of possession and use of the
User Product is transferred to the recipient in perpetuity or for a
fixed term (regardless of how the transaction is characterized), the
Corresponding Source conveyed under this section must be accompanied
by the Installation Information. But this requirement does not apply
if neither you nor any third party retains the ability to install
modified object code on the User Product (for example, the work has
been installed in ROM).
The requirement to provide Installation Information does not include a
requirement to continue to provide support service, warranty, or updates
for a work that has been modified or installed by the recipient, or for
the User Product in which it has been modified or installed. Access to a
network may be denied when the modification itself materially and
adversely affects the operation of the network or violates the rules and
protocols for communication across the network.
Corresponding Source conveyed, and Installation Information provided,
in accord with this section must be in a format that is publicly
documented (and with an implementation available to the public in
source code form), and must require no special password or key for
unpacking, reading or copying.
7. Additional Terms.
"Additional permissions" are terms that supplement the terms of this
License by making exceptions from one or more of its conditions.
Additional permissions that are applicable to the entire Program shall
be treated as though they were included in this License, to the extent
that they are valid under applicable law. If additional permissions
apply only to part of the Program, that part may be used separately
under those permissions, but the entire Program remains governed by
this License without regard to the additional permissions.
When you convey a copy of a covered work, you may at your option
remove any additional permissions from that copy, or from any part of
it. (Additional permissions may be written to require their own
removal in certain cases when you modify the work.) You may place
additional permissions on material, added by you to a covered work,
for which you have or can give appropriate copyright permission.
Notwithstanding any other provision of this License, for material you
add to a covered work, you may (if authorized by the copyright holders of
that material) supplement the terms of this License with terms:
a) Disclaiming warranty or limiting liability differently from the
terms of sections 15 and 16 of this License; or
b) Requiring preservation of specified reasonable legal notices or
author attributions in that material or in the Appropriate Legal
Notices displayed by works containing it; or
c) Prohibiting misrepresentation of the origin of that material, or
requiring that modified versions of such material be marked in
reasonable ways as different from the original version; or
d) Limiting the use for publicity purposes of names of licensors or
authors of the material; or
e) Declining to grant rights under trademark law for use of some
trade names, trademarks, or service marks; or
f) Requiring indemnification of licensors and authors of that
material by anyone who conveys the material (or modified versions of
it) with contractual assumptions of liability to the recipient, for
any liability that these contractual assumptions directly impose on
those licensors and authors.
All other non-permissive additional terms are considered "further
restrictions" within the meaning of section 10. If the Program as you
received it, or any part of it, contains a notice stating that it is
governed by this License along with a term that is a further
restriction, you may remove that term. If a license document contains
a further restriction but permits relicensing or conveying under this
License, you may add to a covered work material governed by the terms
of that license document, provided that the further restriction does
not survive such relicensing or conveying.
If you add terms to a covered work in accord with this section, you
must place, in the relevant source files, a statement of the
additional terms that apply to those files, or a notice indicating
where to find the applicable terms.
Additional terms, permissive or non-permissive, may be stated in the
form of a separately written license, or stated as exceptions;
the above requirements apply either way.
8. Termination.
You may not propagate or modify a covered work except as expressly
provided under this License. Any attempt otherwise to propagate or
modify it is void, and will automatically terminate your rights under
this License (including any patent licenses granted under the third
paragraph of section 11).
However, if you cease all violation of this License, then your
license from a particular copyright holder is reinstated (a)
provisionally, unless and until the copyright holder explicitly and
finally terminates your license, and (b) permanently, if the copyright
holder fails to notify you of the violation by some reasonable means
prior to 60 days after the cessation.
Moreover, your license from a particular copyright holder is
reinstated permanently if the copyright holder notifies you of the
violation by some reasonable means, this is the first time you have
received notice of violation of this License (for any work) from that
copyright holder, and you cure the violation prior to 30 days after
your receipt of the notice.
Termination of your rights under this section does not terminate the
licenses of parties who have received copies or rights from you under
this License. If your rights have been terminated and not permanently
reinstated, you do not qualify to receive new licenses for the same
material under section 10.
9. Acceptance Not Required for Having Copies.
You are not required to accept this License in order to receive or
run a copy of the Program. Ancillary propagation of a covered work
occurring solely as a consequence of using peer-to-peer transmission
to receive a copy likewise does not require acceptance. However,
nothing other than this License grants you permission to propagate or
modify any covered work. These actions infringe copyright if you do
not accept this License. Therefore, by modifying or propagating a
covered work, you indicate your acceptance of this License to do so.
10. Automatic Licensing of Downstream Recipients.
Each time you convey a covered work, the recipient automatically
receives a license from the original licensors, to run, modify and
propagate that work, subject to this License. You are not responsible
for enforcing compliance by third parties with this License.
An "entity transaction" is a transaction transferring control of an
organization, or substantially all assets of one, or subdividing an
organization, or merging organizations. If propagation of a covered
work results from an entity transaction, each party to that
transaction who receives a copy of the work also receives whatever
licenses to the work the party's predecessor in interest had or could
give under the previous paragraph, plus a right to possession of the
Corresponding Source of the work from the predecessor in interest, if
the predecessor has it or can get it with reasonable efforts.
You may not impose any further restrictions on the exercise of the
rights granted or affirmed under this License. For example, you may
not impose a license fee, royalty, or other charge for exercise of
rights granted under this License, and you may not initiate litigation
(including a cross-claim or counterclaim in a lawsuit) alleging that
any patent claim is infringed by making, using, selling, offering for
sale, or importing the Program or any portion of it.
11. Patents.
A "contributor" is a copyright holder who authorizes use under this
License of the Program or a work on which the Program is based. The
work thus licensed is called the contributor's "contributor version".
A contributor's "essential patent claims" are all patent claims
owned or controlled by the contributor, whether already acquired or
hereafter acquired, that would be infringed by some manner, permitted
by this License, of making, using, or selling its contributor version,
but do not include claims that would be infringed only as a
consequence of further modification of the contributor version. For
purposes of this definition, "control" includes the right to grant
patent sublicenses in a manner consistent with the requirements of
this License.
Each contributor grants you a non-exclusive, worldwide, royalty-free
patent license under the contributor's essential patent claims, to
make, use, sell, offer for sale, import and otherwise run, modify and
propagate the contents of its contributor version.
In the following three paragraphs, a "patent license" is any express
agreement or commitment, however denominated, not to enforce a patent
(such as an express permission to practice a patent or covenant not to
sue for patent infringement). To "grant" such a patent license to a
party means to make such an agreement or commitment not to enforce a
patent against the party.
If you convey a covered work, knowingly relying on a patent license,
and the Corresponding Source of the work is not available for anyone
to copy, free of charge and under the terms of this License, through a
publicly available network server or other readily accessible means,
then you must either (1) cause the Corresponding Source to be so
available, or (2) arrange to deprive yourself of the benefit of the
patent license for this particular work, or (3) arrange, in a manner
consistent with the requirements of this License, to extend the patent
license to downstream recipients. "Knowingly relying" means you have
actual knowledge that, but for the patent license, your conveying the
covered work in a country, or your recipient's use of the covered work
in a country, would infringe one or more identifiable patents in that
country that you have reason to believe are valid.
If, pursuant to or in connection with a single transaction or
arrangement, you convey, or propagate by procuring conveyance of, a
covered work, and grant a patent license to some of the parties
receiving the covered work authorizing them to use, propagate, modify
or convey a specific copy of the covered work, then the patent license
you grant is automatically extended to all recipients of the covered
work and works based on it.
A patent license is "discriminatory" if it does not include within
the scope of its coverage, prohibits the exercise of, or is
conditioned on the non-exercise of one or more of the rights that are
specifically granted under this License. You may not convey a covered
work if you are a party to an arrangement with a third party that is
in the business of distributing software, under which you make payment
to the third party based on the extent of your activity of conveying
the work, and under which the third party grants, to any of the
parties who would receive the covered work from you, a discriminatory
patent license (a) in connection with copies of the covered work
conveyed by you (or copies made from those copies), or (b) primarily
for and in connection with specific products or compilations that
contain the covered work, unless you entered into that arrangement,
or that patent license was granted, prior to 28 March 2007.
Nothing in this License shall be construed as excluding or limiting
any implied license or other defenses to infringement that may
otherwise be available to you under applicable patent law.
12. No Surrender of Others' Freedom.
If conditions are imposed on you (whether by court order, agreement or
otherwise) that contradict the conditions of this License, they do not
excuse you from the conditions of this License. If you cannot convey a
covered work so as to satisfy simultaneously your obligations under this
License and any other pertinent obligations, then as a consequence you may
not convey it at all. For example, if you agree to terms that obligate you
to collect a royalty for further conveying from those to whom you convey
the Program, the only way you could satisfy both those terms and this
License would be to refrain entirely from conveying the Program.
13. Use with the GNU Affero General Public License.
Notwithstanding any other provision of this License, you have
permission to link or combine any covered work with a work licensed
under version 3 of the GNU Affero General Public License into a single
combined work, and to convey the resulting work. The terms of this
License will continue to apply to the part which is the covered work,
but the special requirements of the GNU Affero General Public License,
section 13, concerning interaction through a network will apply to the
combination as such.
14. Revised Versions of this License.
The Free Software Foundation may publish revised and/or new versions of
the GNU General Public License from time to time. Such new versions will
be similar in spirit to the present version, but may differ in detail to
address new problems or concerns.
Each version is given a distinguishing version number. If the
Program specifies that a certain numbered version of the GNU General
Public License "or any later version" applies to it, you have the
option of following the terms and conditions either of that numbered
version or of any later version published by the Free Software
Foundation. If the Program does not specify a version number of the
GNU General Public License, you may choose any version ever published
by the Free Software Foundation.
If the Program specifies that a proxy can decide which future
versions of the GNU General Public License can be used, that proxy's
public statement of acceptance of a version permanently authorizes you
to choose that version for the Program.
Later license versions may give you additional or different
permissions. However, no additional obligations are imposed on any
author or copyright holder as a result of your choosing to follow a
later version.
15. Disclaimer of Warranty.
THERE IS NO WARRANTY FOR THE PROGRAM, TO THE EXTENT PERMITTED BY
APPLICABLE LAW. EXCEPT WHEN OTHERWISE STATED IN WRITING THE COPYRIGHT
HOLDERS AND/OR OTHER PARTIES PROVIDE THE PROGRAM "AS IS" WITHOUT WARRANTY
OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO,
THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR
PURPOSE. THE ENTIRE RISK AS TO THE QUALITY AND PERFORMANCE OF THE PROGRAM
IS WITH YOU. SHOULD THE PROGRAM PROVE DEFECTIVE, YOU ASSUME THE COST OF
ALL NECESSARY SERVICING, REPAIR OR CORRECTION.
16. Limitation of Liability.
IN NO EVENT UNLESS REQUIRED BY APPLICABLE LAW OR AGREED TO IN WRITING
WILL ANY COPYRIGHT HOLDER, OR ANY OTHER PARTY WHO MODIFIES AND/OR CONVEYS
THE PROGRAM AS PERMITTED ABOVE, BE LIABLE TO YOU FOR DAMAGES, INCLUDING ANY
GENERAL, SPECIAL, INCIDENTAL OR CONSEQUENTIAL DAMAGES ARISING OUT OF THE
USE OR INABILITY TO USE THE PROGRAM (INCLUDING BUT NOT LIMITED TO LOSS OF
DATA OR DATA BEING RENDERED INACCURATE OR LOSSES SUSTAINED BY YOU OR THIRD
PARTIES OR A FAILURE OF THE PROGRAM TO OPERATE WITH ANY OTHER PROGRAMS),
EVEN IF SUCH HOLDER OR OTHER PARTY HAS BEEN ADVISED OF THE POSSIBILITY OF
SUCH DAMAGES.
17. Interpretation of Sections 15 and 16.
If the disclaimer of warranty and limitation of liability provided
above cannot be given local legal effect according to their terms,
reviewing courts shall apply local law that most closely approximates
an absolute waiver of all civil liability in connection with the
Program, unless a warranty or assumption of liability accompanies a
copy of the Program in return for a fee.
END OF TERMS AND CONDITIONS